## Sheet1
TEST PLAN For nopCommerce
Sr. No | Module Name | Test Plan ID | Introduction | Test Items | Features to be Tested | Features Not Tested | Approach | Environment | Test Deliverables | Pass/Fail Criteria | Suspension Criteria | Staffing and Training | Responsibility | Schedule | Risk/Contingency | Approval
1 | Register | TP-NopCommerce-REG-001 | Validate user registration flow with mandatory and optional fields. | First name, Last name Gender radio buttons, Email , company name , newsletter checkbox, password , confirm password, register button, categories, header section, footer section Links, nopcommerce logo | Gender radio buttons, First name , Last name , Email field, password , confirm password, register button | newsletter checkbox, nopcommerce logo, Categories, Footer links (Privacy Notice, Newsletter, Blog, etc.) | Manual + Automation (Selenium) | Website URL , Windows 10/11, MacOS, Linux, Android/iOS, Browsers (Chrome, Firefox, Edge, Brave) | Test Plan Test Cases (Excel/Jira) Test Reports Defect Reports | Pass -all mandatory fields accept valid input, account created. | NA | Selenium WebDriver, TestNG, Cucumber | Prasenjit Bhosale (Tester) | 2025-08-28 | No Risk | Vaishali Sonanis
2 | Login | TP-NopCommerce-LOG-002 | Verify authentication and session handling for registered users. | Authentication and session handling for registered users. | Login with valid credentials, Invalid login (wrong password/email), Remember me, Forget Password, Login Button | new customer option, Forgot password link, Footer links | Manual + Automation (Selenium) | Website URL , Windows 10/11, MacOS, Linux, Android/iOS, Browsers (Chrome, Firefox, Edge, Brave) | Test cases Report Test Plan Test Summary Report Test Bug Report Test Analysis Report Review documents Bug Analysis report etc | Pass - valid credentials - > log in successfully. Fail - invalid cases not handled. | NA | Selenium WebDriver, TestNG, Cucumber | Prasenjit Bhosale (Tester) | 2025-08-28 | No Risk | Vaishali Sonanis
3 | Search | TP-NopCommerce-SRCH-003 | Ensure search functionality retrieves correct products using keywords and filters. | SearchBar, Search Button, Filter By Price, Adance Search checkbox, Sort By Filter, Display Per Page filter, List View, Grid View, Recently Viewed Products, Popular Tags | Searchbar, Search Button, Filter By Price, | Advanced Search Filter | Manual + Automation (Selenium) | Website URL , Windows 10/11, MacOS, Linux, Android/iOS, Browsers (Chrome, Firefox, Edge, Brave) | Test cases Report Test Plan Test Summary Report Test Bug Report Test Analysis Report Review documents Bug Analysis report etc | Pass - results match search keyword/filter. Fail - mismatch/no response. | NA | Selenium WebDriver, TestNG, Cucumber | Prasenjit Bhosale (Tester) | 2025-08-28 | No Risk | Vaishali Sonanis
4 | Home Page | TP-NopCommerce-HP-004 | Validate accessibility of navigation links, featured products, and header/footer components. | Test navigation bar, search, register, login, wishlist, cart, currency converter, image slider, featured products, social links, contact us, newsletter. | Navigation Bar, Search Bar, Login, Wishlist, Cart, Currency Converter, Image Slider, NewsLetter, Footer Social Links | News, Community Poll, Digital Downloads section | Manual + Automation (Selenium) | Website URL , Windows 10/11, MacOS, Linux, Android/iOS, Browsers (Chrome, Firefox, Edge, Brave) | Test cases Report Test Plan Test Summary Report Test Bug Report Test Analysis Report Review documents Bug Analysis report etc | Pass - all links/navigations work. Fail - links dont work | NA | Selenium WebDriver, TestNG, Cucumber | Prasenjit Bhosale (Tester) | 2025-08-28 | No Risk | Vaishali Sonanis
5 | Cart | TP-NopCommerce-CRT-005 | Confirm cart operations like add, remove, update quantity, and apply discounts/coupons. | Add item to cart, remove item, update quantity, apply discount/gift card, enable gift wrapping, Checkout, product image, product price, ratings, add to compare list button, add to wishlist button, | Add/Remove Items, Update Quantity, Discount Code, Gift Card, Gift Wrapping, Checkout | product image, product price, ratings, add to compare list button, add to wishlist button, Footer links | Manual + Automation (Selenium) | Website URL , Windows 10/11, MacOS, Linux, Android/iOS, Browsers (Chrome, Firefox, Edge, Brave) | Test cases Report Test Plan Test Summary Report Test Bug Report Test Analysis Report Review documents Bug Analysis report etc | Pass - cart reflects all actions correctly. Fail - cart doesnt't work properly | NA | Selenium WebDriver, TestNG, Cucumber | Prasenjit Bhosale (Tester) | 2025-08-28 | No Risk | Vaishali Sonanis
6 | Wishlist | TP-NopCommerce-WLST-006 | Verify wishlist functionality including add, update, and move items to cart. | Add items to wishlist, update wishlist, move to cart, update quantity, verify wishlist URL. | Add to Wishlist, Update Wishlist, Add to Cart from Wishlist, Update Quantity, Wishlist URL | Footer links , Popular Tags Link | Manual + Automation (Selenium) | Website URL , Windows 10/11, MacOS, Linux, Android/iOS, Browsers (Chrome, Firefox, Edge, Brave) | Test cases Report Test Plan Test Summary Report Test Bug Report Test Analysis Report Review documents Bug Analysis report etc | Pass - wishlist retains and updates items. Fail - wishlist data is lost. | NA | Selenium WebDriver, TestNG, Cucumber | Prasenjit Bhosale (Tester) | 2025-08-28 | No Risk | Vaishali Sonanis
7 | Shop By Category | TP-NopCommerce-SBC-007 | Ensure category and subcategory navigation loads relevant products. | Category Navigation, Subcategory Navigation, Deep filter combinations | Category Navigation, Subcategory Navigation | Deep filter combinations | Manual + Automation (Selenium) | Website URL , Windows 10/11, MacOS, Linux, Android/iOS, Browsers (Chrome, Firefox, Edge, Brave) | Test cases Report Test Plan Test Summary Report Test Bug Report Test Analysis Report Review documents Bug Analysis report etc | Pass - categories load with products. Fail - broken/missing navigation. | NA | Selenium WebDriver, TestNG, Cucumber | Prasenjit Bhosale (Tester) | 2025-08-28 | No Risk | Vaishali Sonanis
8 | Computers Category | TP-NopCommerce-COMP-008 | Validate navigation to Computers category and its subcategories with proper product catalog display. | Category links (Desktops, Notebooks, Software), Product Page, Filter Modal, Sort By, List/Grid View. | Subcategory navigation, Product catalog display, Sorting, Filtering, Pagination. | Advance filter combinations, Footer Links, Popular Tags Link | Manual + Automation (Selenium) | Website URL , Windows 10/11, MacOS, Linux, Android/iOS, Browsers (Chrome, Firefox, Edge, Brave) | Test cases Report Test Plan Test Summary Report Test Bug Report Test Analysis Report Review documents Bug Analysis report etc | Pass if all functinalties work as expected | NA | Selenium WebDriver, TestNG, Cucumber | Prasenjit Bhosale (Tester) | 2025-08-28 | No Risk | Vaishali Sonanis
9 | Electronics Category | TP-NopCommerce-ELC-009 | Ensure Electronics category navigation works correctly with all subcategories and product listings. | Subcategory Links (Cameras, Cell Phones, Others), Product Page, Filter Modal, Sort By, List/Grid View. Add To Cart, Compare,Wishlist | Category navigation, Subcategory navigation, Sorting, Filtering, Pagination. | Advance filter combinations, Footer Links | Manual + Automation (Selenium) | Website URL , Windows 10/11, MacOS, Linux, Android/iOS, Browsers (Chrome, Firefox, Edge, Brave) | Test cases Report Test Plan Test Summary Report Test Bug Report Test Analysis Report Review documents Bug Analysis report etc | Pass if all functinalties work as expected | NA | Selenium WebDriver, TestNG, Cucumber | Prasenjit Bhosale (Tester) | 2025-08-28 | No Risk | Vaishali Sonanis
10 | Apparel Category | TP-NopCommerce-APRL-010 | Validate Apparel category navigation with all subcategories and product listings. | Subcategory Links (Shoes, Clothing, Accessories), Filter Modal, Sort By, List/Grid View, Product Catalog Display. Add To Cart, Compare,Wishlist, Manufacture | Subcategory navigation, Product catalog display, Sorting, Filtering, Pagination. | Footer Links, Popular Tags Link | Manual + Automation (Selenium) | Website URL , Windows 10/11, MacOS, Linux, Android/iOS, Browsers (Chrome, Firefox, Edge, Brave) | Test cases Report Test Plan Test Summary Report Test Bug Report Test Analysis Report Review documents Bug Analysis report etc | Pass - apparel subcategories display relevant products. Fail - navigation/catalog not loading properly. | NA | Selenium WebDriver, TestNG, Cucumber | Prasenjit Bhosale (Tester) | 2025-08-28 | No Risk | Vaishali Sonanis
11 | Digital Downloads Category | TP-NopCommerce-DDC-011 | Ensure Digital Downloads Navigation Works | Filter Modal, Sort By, List/Grid View, Product Catalog Display, Add To Cart, Compare,Wishlist, Category Links | Product catalog display, Sorting, Filtering, Pagination, Add to Cart, Compare, Wishlist | Footer Links, Manufacture , Popular Tags Link | Manual + Automation (Selenium) | Website URL , Windows 10/11, MacOS, Linux, Android/iOS, Browsers (Chrome, Firefox, Edge, Brave) | Test cases Report Test Plan Test Summary Report Test Bug Report Test Analysis Report Review documents Bug Analysis report etc | Pass if all functinalties work as expected | NA | Selenium WebDriver, TestNG, Cucumber | Prasenjit Bhosale (Tester) | 2025-08-28 | No Risk | Vaishali Sonanis
12 | Books Category | TP-NopCommerce-BKS-012 | Ensure Books Category Navigation Works | Filter Modal, Sort By, List/Grid View, Product Catalog Display, Add To Cart, Compare,Wishlist, Category Links, Manufacture | Product catalog display, Sorting, Filtering, Pagination, Add to Cart, Compare, Wishlist | Manufacture ,Footer Links, Popular Tags Link | Manual + Automation (Selenium) | Website URL , Windows 10/11, MacOS, Linux, Android/iOS, Browsers (Chrome, Firefox, Edge, Brave) | Test cases Report Test Plan Test Summary Report Test Bug Report Test Analysis Report Review documents Bug Analysis report etc | Pass if all functinalties work as expected | NA | Selenium WebDriver, TestNG, Cucumber | Prasenjit Bhosale (Tester) | 2025-08-28 | No Risk | Vaishali Sonanis
13 | Jewelry Category | TP-NopCommerce-JWR-013 | Ensure Jewelry Category Navigation Works and Add to cart and RENT | Rent, Add to Cart, Compare,Wishlist, Filter Modal, Sort By, List/Grid View, Product Catalog Display, Manufacture | Rent, Product catalog display, Sorting, Filtering, Pagination, Add to Cart, Compare, Wishlist,List/Grid View, | Manufacture ,Footer Links, Popular Tags Link | Manual + Automation (Selenium) | Website URL , Windows 10/11, MacOS, Linux, Android/iOS, Browsers (Chrome, Firefox, Edge, Brave) | Test cases Report Test Plan Test Summary Report Test Bug Report Test Analysis Report Review documents Bug Analysis report etc | Pass if all functinalties work as expected | NA | Selenium WebDriver, TestNG, Cucumber | Prasenjit Bhosale (Tester) | 2025-08-28 | No Risk | Vaishali Sonanis
14 | Gift Cards Category | TP-NopCommerce-GFT-014 | Ensure Gift Cards category navigation works along with gift card purchase functionality. | Git card Product description, Recipient's Name,Recipient's Email, Your Name,Your Email, Message,Add to Cart, Compare,Wishlist, Filter Modal, Sort By, List/Grid View, Product Catalog Display, | Sample Review, Gift card product details, Recipient's Name,Recipient's Email, Your Name,Your Email, Add to Cart, Compare, Wishlist, Catalog display, Sorting, Filtering, Pagination | Footer Links, Popular Tags Link | Manual + Automation (Selenium) | Website URL , Windows 10/11, MacOS, Linux, Android/iOS, Browsers (Chrome, Firefox, Edge, Brave) | Test cases Report Test Plan Test Summary Report Test Bug Report Test Analysis Report Review documents Bug Analysis report etc | Pass if all functinalties work as expected | NA | Selenium WebDriver, TestNG, Cucumber | Prasenjit Bhosale (Tester) | 2025-08-28 | No Risk | Vaishali Sonanis